## Status(Summary)
Date | Phase | Outline | Comments
2020-02-07 | Prelimnary Analysis | Overview of topic | 1) Implement a survey engine parser in dart for a given data model 2) Use Influenzanet survey engine from github public repo 3) Received survey model diagram with datatypes 4) Goal of the thesis would be to implement the survey engine model in dart and package it as a flutter extension. A flutter sample app should be able to use the package to render survey components. 5) The dart engine can further be modified to use sensor data from the smartphone as an input to render surveys. 6) Implement Expression,SurveyItem class from the survey model diagram and come up with clarifications. 7) Follow TDD approach for software development
2020-02-12 | Prelimnary Analysis | Clarifications for queries | 1) Goal of the thesis is as understood 2) More idea of survey component rendering in expression as the development builds 3) Use 'num' from json then convert to number 4) New repo created for survey engine.dart in github
2020-02-19 | Implementation | Expression evaluation | 1) Classes and subclasses for Expression evaluation written 2) Logical and Relational expression evaluations written for operators evaluating boolean return types like and,or,eq,lt,lte,gt etc 3) Unit tests written for the same
2020-02-27 | Implementation | Expression evaluation and Component study | 1) Expression evaluation for combination of operators 2) Further changes to expression evaluation after Q & A 3) Identifying the next tasks 4) Creation of query document in md (https://github.com/influenzanet/survey-engine.dart/blob/development/documents/QandA.md) 5) Implementation of LocalisedMediaObject 6) Implementation of DisplayComponent started
2020-03-06 | Implementation | Item Component creation and Survey ItemComponent study | 1) Created ItemComponent classes and subclasses based on UML feedback. 2) Using a concept of `factory` constructors inheritance through interfaces implementation taken care of. 3) Initial outline questions on front-end/backend evaluation and plugin package automation. 4) Updated Q and A markdown file To do: 1) Complete Survey Item Components outline next and start engine implementation 2) Create a wiki on all learnings. A small dump is also fine
2020-03-12 | Implementation | SurveyComponent implementation | 1) Implemented and tested SurveyComponent outline classes 2) Implemented SurveyResponseItem outline classes completing ouline of all respective class models in the Survey 3) Studied expression-eval, engine.ts and made notes of doubts 4) resolveContent in LocalisedObject expression implemented internally during the object creation 5) SelectionMethod implemented for a dummy map of array items 6) Created an issue for a `wiki` page. Will be updating in due course of `engine` development

## Q & As
Date | Queries | Clarifications
2020-02-12 | 1) An example of survey item with expression eval workflow 2) Can 'num' be changed to 'number' attribute in ExpressionArg 3) Feedback on prelimnary code | 1) Look at test-surveys module in typescript for example JSON 2) Render num as string later on 3) Clean code and use new github dart repository
2020-02-18 | 1) How are "OR" and "AND" evaluated for other numbers 2) How are "OR" and "AND" evaluated for string values 3) If "OR" and "AND" contains evaluates an `Expression` type object and return a non bool value, how can they be evaluated. 4) How does "isDefined" function work? | 1) Evaluate 0 as false and any other number as true 2) Evaluate empty string as false and any other string as true 3) The incoming JSON file is assumed to be valid as checks on validity of each dataType and returnType would feel too large 4) "isDefined" function checks a resulting value of expression is not null, thereby testing the validty of the expression
2020-02-19 | 1) Should validity of expression be checked for eg: how would ((2<3)<5) be evaluated?. | 1) The incoming JSON file is assumed to be valid as checks on validity of each dataType and returnType would feel too large
2020-02-23 | 1) isDefined function tests are written only for certain functions of `exp` type. Should testExpr = { 'name': 'isDefined', 'data': [{'dType': 'number', 'str': '5'}}; return a `false` ? | 1) It comes under Survey Item Components ask back after Survey Item Component implementation
2020-02-24 | 1) Queries related to Item Component implementation (https://github.com/influenzanet/survey-engine.dart/blob/development/documents/QandA.md) | 1) Refer https://github.com/influenzanet/survey-engine.ts/wiki/Components-of-a-survey-item#components-of-a-survey-item for documentation overview