## Status(Summary)
Date | Phase | Outline | Comments
2020-02-07 | Prelimnary Analysis | Overview of topic | 1) Implement a survey engine parser in dart for a given data model 2) Use Influenzanet survey engine from github public repo 3) Received survey model diagram with datatypes 4) Goal of the thesis would be to implement the survey engine model in dart and package it as a flutter extension. A flutter sample app should be able to use the package to render survey components. 5) The dart engine can further be modified to use sensor data from the smartphone as an input to render surveys. 6) Implement Expression,SurveyItem class from the survey model diagram and come up with clarifications. 7) Follow TDD approach for software development
2020-02-12 | Prelimnary Analysis | Clarifications for queries | 1) Goal of the thesis is as understood 2) More idea of survey component rendering in expression as the development builds 3) Use 'num' from json then convert to number 4) New repo created for survey engine.dart in github
2020-02-19 | Implementation | Expression evaluation | 1) Classes and subclasses for Expression evaluation written 2) Logical and Relational expression evaluations written for operators evaluating boolean return types like and,or,eq,lt,lte,gt etc 3) Unit tests written for the same
2020-02-27 | Implementation | Expression evaluation and Component study | 1) Expression evaluation for combination of operators 2) Further changes to expression evaluation after Q & A 3) Identifying the next tasks 4) Creation of query document in md (https://github.com/influenzanet/survey-engine.dart/blob/development/documents/QandA.md) 5) Implementation of LocalisedMediaObject 6) Implementation of DisplayComponent started
2020-03-06 | Implementation | Item Component creation and Survey ItemComponent study | 1) Created ItemComponent classes and subclasses based on UML feedback. 2) Using a concept of `factory` constructors inheritance through interfaces implementation taken care of. 3) Initial outline questions on front-end/backend evaluation and plugin package automation. 4) Updated Q and A markdown file To do: 1) Complete Survey Item Components outline next and start engine implementation 2) Create a wiki on all learnings. A small dump is also fine
2020-03-12 | Implementation | SurveyComponent implementation | 1) Implemented and tested SurveyComponent outline classes 2) Implemented SurveyResponseItem outline classes completing ouline of all respective class models in the Survey 3) Studied expression-eval, engine.ts and made notes of doubts 4) resolveContent in LocalisedObject expression implemented internally during the object creation 5) SelectionMethod implemented for a dummy map of array items 6) Created an issue for a `wiki` page. Will be updating in due course of `engine` development
2020-03-25 | Implementation | SurveyEngineCore Implementation | 1) Survey Engine Core Implementation started 2) Identified the first few functions to be implemented - resolveContent - resolveItemGroupComponent - renderSurveySingleItem 3) Fixed bugs in resolving Null paramenters on object creation also on toMap,fromMap creation 4) getAttribute, getContext evaulation queries asked and getContext in expression-evaluation implemented 5) selection method and random distribution expressions implemented will be worked again later in due course after some more discussions 6) Expression Evaluation `wiki` implemented 7) TO DO: initResponseObject->constructor->findResponseItem->setTimestampFor->addRenderedItem
2020-03-26 | Implementation | SurveyEngineCore Implementation | 1) Discussion on upcoming queries 2) Wrote a few flowcharts for surveyEngine like constructor,setTimestampFor,addRenderedItem and will be changed after some reviews 3) Implemented `setTimeStampFor` function and tests
2020-04-02 | Discussion | Flowchart creation and queries | 1) Status and test cases shown 2) Flowchart presented -- review opinion rework on flowchart and remove pseudo code from flowchart 3) Hierarchy present for groups and single item keys
2020-04-09 | Implementation | SurveyEngineCore Implementation | 1) Studied findResponse, Rendered Item 2) Watched the control flow of init objects and deduced an algorithm thereby translating the constructor creation of Survey Engine 3) Every ItemGroupComponent every single survey Item and every response Item is created as well as resolved (excluding rerender functions and expressions using rerender objects) in a sequential order 4) Optimised the algorithm for fewer checks and wrote utility functions like getRootKey, removeNullparams etc for better clean code concepts as well as improving readability. 5) Fixed major bugs relating to itemgroup component resolution and rendering Survey Group Component items and few others relating to validations, parts resolution etc 6) Flowcharts rewritten with an abstract view by not including pseudocde until the reordering/rerendering of functions 7) Updated query sheet and informed about freezing model==0.4.9 for now. The version will be implemeneted and tested then upcoming changes will be rendered appropriately according to time constraint
2020-04-16 | Implementation | SurveyEngineCore Implementation and flowchart creation | 1) Bug fixes. Fixed bugs relating to rendering survey trees. The order of Maps and JSON in some components and models were different are fixed 2) Studying initRenderGroup function and a flowchart written for the same 3) Changed implementation strategy to modularise functions like getItemsWithFollows, getUnrenderedItems etc. Clean code strategy used for better understanding. 4) Numerous test cases written for each of the new private function to make sure the order of the survey group items are working as expected even in nested groups 5) Updated a rough wiki for developer notes and pitfalls while implementing survey engine in a server side and typestrict language https://github.com/influenzanet/survey-engine.dart/wiki/Notes
2020-04-23 | Analysis and implementation | SurveyEngineCore Implementation | 1) initRenderedGroup and initSurveyresponseObjects completed. i.e the survey-engine parses conditions, evalConditions and renders the first set of Responses along with items and components in the initial step 2) Implemented `sequential` in selection methods to make testing easy. The survey group items are picked randomly by default and was a harder to compare the structure with test objects so `sequential` is used as a workaroud default for now 3) Came up with 5 theme names for the Master thesis topic 4) Public methods for getting a rendered survey and getting responses in flat tree done
2020-04-30 | Analysis, implementation and documentation | Expression Evaluation | 1) Studied setResponseItem and started reRender studies 2) On careful analysis realised that expression evaluation needs to be completed for rerendering. Without a valid getResponses a setResponse would make not much sense 3) Studied all Array,Object and tree expressions. 4) Created a wiki for the same expressions 5) Implemented all the expressions and tested it in various scenarios. Testing can be improved. 6) Queries updated 7) Thesis topic name finalised as "Analysis of the survey model and implementation of a survey engine for parsing survey components of the Influenzanet project on a smartphone screen: A Dart library for developing cross-platform flutter applications"

## Q & As
Date | Queries | Clarifications
2020-02-12 | 1) An example of survey item with expression eval workflow 2) Can 'num' be changed to 'number' attribute in ExpressionArg 3) Feedback on prelimnary code | 1) Look at test-surveys module in typescript for example JSON 2) Render num as string later on 3) Clean code and use new github dart repository
2020-02-18 | 1) How are "OR" and "AND" evaluated for other numbers 2) How are "OR" and "AND" evaluated for string values 3) If "OR" and "AND" contains evaluates an `Expression` type object and return a non bool value, how can they be evaluated. 4) How does "isDefined" function work? | 1) Evaluate 0 as false and any other number as true 2) Evaluate empty string as false and any other string as true 3) The incoming JSON file is assumed to be valid as checks on validity of each dataType and returnType would feel too large 4) "isDefined" function checks a resulting value of expression is not null, thereby testing the validty of the expression
2020-02-19 | 1) Should validity of expression be checked for eg: how would ((2<3)<5) be evaluated?. | 1) The incoming JSON file is assumed to be valid as checks on validity of each dataType and returnType would feel too large
2020-02-23 | 1) isDefined function tests are written only for certain functions of `exp` type. Should testExpr = { 'name': 'isDefined', 'data': [{'dType': 'number', 'str': '5'}}; return a `false` ? | 1) It comes under Survey Item Components ask back after Survey Item Component implementation
2020-02-24 | 1) Queries related to Item Component implementation (https://github.com/influenzanet/survey-engine.dart/blob/development/documents/QandA.md) | 1) Refer https://github.com/influenzanet/survey-engine.ts/wiki/Components-of-a-survey-item#components-of-a-survey-item for documentation overview